## Summary Log
PSP0 Summary Log
CPSC 280: Introduction to Software Engineering
Assignment #1
Name: | Alexander MacLeod
ID: | 00957731
Times Summary
Total time spent on each phase (in minutes)
|  | Planned | Actual | %
| Analysis |  | 37 | 4.358%
| Design |  | 90 | 10.6%
| Implementation |  | 559 | 65.84%
| Testing |  | 163 | 19.2%
| TOTAL | 240 | 849 | 100%
Errors Summary
Errors found on each phase (in number)
|  | Actual | %
| Analysis | 0 | 0%
| Design | 1 | 5.263%
| Implementation | 13 | 68.42%
| Testing | 5 | 26.32%
| TOTAL | 19 | 100%
Errors fixed on each phase (in number)
|  | Actual | %
| Analysis | 0 | 0%
| Design | 0 | 0%
| Implementation | 8 | 42.11%
| Testing | 11 | 57.89%
| TOTAL | 19 | 100%

## Time Log
PSP0 Time Log
CPSC 280: Introduction to Software Engineering
Assignment #1
Name: | Alexander MacLeod
ID: | 00957731
Time Entries
EXAMPLE
0 | Design | 2018-11-05 08:15 | 2018-11-05 09:29 | 2 | 72 | Identified data structures needed (map & list). Mom texted.
Interruptions
| Phase | Start Date/Time | End Date/Time | (in minutes) | Actual | Comments
1 | Analysis | 2020-09-04 11:45 | 2020-09-04 11:48 | 0 | 3 | First read of assignment description.
2 | Analysis | 2020-09-05 18:11 | 2020-09-05 18:14 | 0 | 3 | Deciding what guards are needed for program.
3 | Analysis | 2020-09-09 12:06 | 2020-09-09 12:42 | 5 | 31 | Took apart assignment sheet and got confused on implementation part. Scheduled office hours. Interruptions from eating
4 | Design | 2020-09-09 23:05 | 2020-09-10 00:35 | 0 | 90 | Created flow chart, began thinking of most efficient way to code
5 | Implementation | 2020-09-11 16:45 | 2020-09-11 18:08 | 0 | 83 | Started to code, ran into issues with getting tags that are already closed out.
6 | Implementation | 2020-09-12 01:26 | 2020-09-12 02:43 | 0 | 77 | Started to solve test cases, but realized I ws getting too specific with my solutions for test cases.
7 | Implementation | 2020-09-12 12:18 | 2020-09-12 13:35 | 0 | 77 | Refactored some code, but still failing some tests.
8 | Implementation | 2020-09-13 13:30 | 2020-09-13 14:46 | 0 | 76 | finally implemented algorithm that puts tags into arraylist, if the tag gets closed before end index it removes it.
9 | Implementation | 2020-09-13 16:00 | 2020-09-13 20:36 | 30 | 246 | Ran into a lot of issues with the closing tags. Had to start a new algorithm, which is actually less code than before. Ate.
10 | Testing | 2020-09-14 12:10 | 2020-09-14 12:45 | 0 | 35 | Began testing code. Debugging.
11 | Testing | 2020-09-14 17:55 | 2020-09-14 18:58 | 0 | 63 | All tests finally pass! I feel like code can be refactored though. Added comments. Renamed some variable for readability.
12 | Testing | 2020-09-15 12:00 | 2020-09-15 12:20 | 0 | 20 | Went to office hours to learn to refactor code. Refactored one chunk of code that gets open tags.
13 | Testing | 2020-09-16 17:30 | 2020-09-16 18:20 | 5 | 45 | Refactored rest of code. Conversing with roommates.
14 |  |  |  |  | 0
15 |  |  |  |  | 0
16 |  |  |  |  | 0
17 |  |  |  |  | 0
18 |  |  |  |  | 0
19 |  |  |  |  | 0
20 |  |  |  |  | 0
21 |  |  |  |  | 0
22 |  |  |  |  | 0
23 |  |  |  |  | 0
24 |  |  |  |  | 0
25 |  |  |  |  | 0
26 |  |  |  |  | 0
27 |  |  |  |  | 0
28 |  |  |  |  | 0
29 |  |  |  |  | 0
30 |  |  |  |  | 0
31 |  |  |  |  | 0
32 |  |  |  |  | 0
33 |  |  |  |  | 0
34 |  |  |  |  | 0
35 |  |  |  |  | 0
36 |  |  |  |  | 0
37 |  |  |  |  | 0
38 |  |  |  |  | 0
39 |  |  |  |  | 0
40 |  |  |  |  | 0
41 |  |  |  |  | 0
42 |  |  |  |  | 0
43 |  |  |  |  | 0
44 |  |  |  |  | 0
45 |  |  |  |  | 0
46 |  |  |  |  | 0
47 |  |  |  |  | 0
48 |  |  |  |  | 0
49 |  |  |  |  | 0
50 |  |  |  |  | 0

## Errors Log
PSP0 Errors Log
CPSC 280: Introduction to Software Engineering |  |  |  |  | Error Types
Assignment #1 |  |  |  |  | Compile | Compile error takes 30+ seconds to fix
[5 empty] | Logic | Misinterpreting or incorrectly implementing (Requirements¦Specification¦Design¦Code)
Name: | Alexander MacLeod |  |  |  | System | Device (Computer¦Network) or Environment (OS¦JDK¦Eclipse¦git) is missing, misconfigured, used improperly or malfunctioning
ID: | 00957731
Error Entries
EXAMPLE
0 | 2018-11-05 22:42 | Compile | Design | Implementation | 15 | Wrote Comparator objects to sort using different criteria (Comparable only allows for 1 criteria).
Time to Fix
| Happening Time | Type | Inserted | Removed | (in minutes) | Description
1 | 2020-09-10 | Compile | Design | Implementation | 5 | Wrote a while loop that created an infinite loop, removed and found a workaround to the issue.
2 | 2020-09-12 02:26 | Logic | Implementation | Implementation | 25 | Passes some tests, but other tests are failing.
3 | 2020-09-13 12:13 | Compile | Implementation | Implementation | 1 | Index out of bounds exception.
4 | 2020-09-13 13:45 | Logic | Implementation | Implementation | 15 | Code became too complex and hard to read. Started failing more tests than before.
5 | 2020-09-13 14:03 | Logic | Implementation | Implementation | 10 | Tests that had end index as end of string were failing tests because program would add on end tags. Fixed.
6 | 2020-09-13 14:34 | Compile | Implementation | Implementation | 3 | Null pointer exception for strArray.
7 | 2020-09-13 14:39 | Compile | Implementation | Implementation | 5 | Null pointer exception for messageArr.
8 | 2020-09-13 16:54 | Compile | Implementation | Implementation | 3 | Index out of bounds exception.
9 | 2020-09-13 17:21 | Logic | Implementation | Testing | 20 | Code was not doing what I expected it to do, like getting the right substring. Did some debugging to fix logic error.
10 | 2020-09-13 18:00 | Compile | Implementation | Testing | 4 | Entered the wrong values for function.
11 | 2020-09-13 18:35 | Logic | Implementation | Testing | 30 | Failing 3 tests. Got them to pass after rewriting loop.
12 | 2020-09-13 18:42 | Logic | Implementation | Testing | 20 | New tests failing but organized code to be more readable.
13 | 2020-09-13 18:44 | System | Implementation | Testing | 4 | Eclipse crashed.
14 | 2020-09-13 19:37 | Compile | Implementation | Testing | 3 | Index out of bounds exception.
15 | 2020-09-13 19:55 | Compile | Testing | Testing | 2 | Index out of bounds exception.
16 | 2020-09-14 18:10 | Compile | Testing | Testing | 1 | Index out of bounds exception.
17 | 2020-09-14 18:25 | Logic | Testing | Testing | 15 | One test failing. When index is whole string.
18 | 2020-09-14 18:25 | Logic | Testing | Testing | 30 | Couldn’t figure out how to handle when index was the end of string, but fixed it with a guard for if end==string.length, break the loop.
19 | 2020-09-16 18:00 | Compile | Testing | Testing | 2 | While refactoring got an error when I forgot a line of code.
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50